## Overview
Timeline | XH-01
2050-03-01 | Construction
2050-04-01
2050-05-01
2050-06-01
2050-07-01
2050-08-01
2050-09-01
2050-10-01
2050-11-01
2050-12-01
2051-01-01
2051-02-01
2051-03-01
2051-04-01
2051-05-01
2051-06-01
2051-07-01
2051-08-01
2051-09-01
2051-10-01
2051-11-01
2051-12-01
2052-01-01
2052-02-01
2052-03-01 | Fitting
2052-04-01
2052-05-01
2052-06-01 | Trial Run
2052-07-01
2052-08-01
2052-09-01
2052-10-01
2052-11-01
2052-12-01 | Maintenance
2053-01-01
2053-02-01 | Deep Space Test Mission
2053-03-01
2053-04-01
2053-05-01
2053-06-01
2053-07-01
2053-08-01
2053-09-01
2053-10-01
2053-11-01
2053-12-01
2054-01-01 | Maintenance and upgrades
2054-02-01
2054-03-01
2054-04-01
2054-05-01
2054-06-01
2054-07-01 | Mars Mission Demo Outbound
2054-08-01
2054-09-01 | Mars Mission Demo at Mars
2054-10-01
2054-11-01
2054-12-01
2055-01-01
2055-02-01 | Mars Mission Demo Return to Earth
2055-03-01 | Maintenance and upgrade
2055-04-01
2055-05-01
2055-06-01 | Mars One base construction mission 1 outbound
2055-07-01
2055-08-01 | Mars One base construction mission 1 at Mars
2055-09-01
2055-10-01
2055-11-01
2055-12-01
2056-01-01
2056-02-01
2056-03-01 | Maintenance and upgrades
2056-04-01
2056-05-01
2056-06-01
2056-07-01 | Mars One base construction mission 3
2056-08-01
2056-09-01
2056-10-01 | Mars One base construction mission 3
2056-11-01
2056-12-01
2057-01-01
2057-02-01
2057-03-01 | Maintenance
2057-04-01
2057-05-01 | Mars Expedition 2 Outbound
2057-06-01
2057-07-01 | Mars Expedition 2 at Mars
2057-08-01
2057-09-01
2057-10-01
2057-11-01
2057-12-01
2058-01-01
2058-02-01
2058-03-01
2058-04-01
2058-05-01 | Maintenance
2058-06-01
2058-07-01 | Europa Expedition 1 Outbound
2058-08-01
2058-09-01
2058-10-01 | Europa Expedition 1 at Jupiter System
2058-11-01
2058-12-01
2059-01-01
2059-02-01
2059-03-01
2059-04-01
2059-05-01
2059-06-01
2059-07-01
2059-08-01 | Europa Expedition 1 Return to Earth
2059-09-01
2059-10-01
2059-11-01
2059-12-01 | Maintenance and upgrade
2060-01-01
2060-02-01
2060-03-01 | Europa Expedition 3 Outbound
2060-04-01
2060-05-01
2060-06-01
2060-07-01
2060-08-01
2060-09-01
2060-10-01
2060-11-01
2060-12-01
2061-01-01
2061-02-01
2061-03-01
2061-04-01
2061-05-01
2061-06-01
2061-07-01
2061-08-01
2061-09-01
2061-10-01
2061-11-01
2061-12-01
2062-01-01
2062-02-01
2062-03-01
2062-04-01
2062-05-01
2062-06-01
2062-07-01
2062-08-01
2062-09-01
2062-10-01
2062-11-01
2062-12-01
2063-01-01
2063-02-01
2063-03-01
2063-04-01
2063-05-01
2063-06-01
2063-07-01
2063-08-01
2063-09-01
2063-10-01
2063-11-01
2063-12-01
2064-01-01
2064-02-01
2064-03-01
2064-04-01
2064-05-01
2064-06-01
2064-07-01
2064-08-01
2064-09-01
2064-10-01
2064-11-01
2064-12-01
2065-01-01
2065-02-01
2065-03-01
2065-04-01
2065-05-01
2065-06-01
2065-07-01
2065-08-01
2065-09-01
2065-10-01
2065-11-01
2065-12-01
2066-01-01
2066-02-01
2066-03-01
2066-04-01
2066-05-01
2066-06-01
2066-07-01
2066-08-01
2066-09-01
2066-10-01
2066-11-01
2066-12-01
2067-01-01
2067-02-01
2067-03-01
2067-04-01
2067-05-01
2067-06-01
2067-07-01
2067-08-01
2067-09-01
2067-10-01
2067-11-01
2067-12-01
2068-01-01
2068-02-01
2068-03-01
2068-04-01
2068-05-01
2068-06-01
2068-07-01
2068-08-01
2068-09-01
2068-10-01
2068-11-01
2068-12-01
2069-01-01
2069-02-01
2069-03-01
2069-04-01
2069-05-01
2069-06-01
2069-07-01
2069-08-01
2069-09-01
2069-10-01
2069-11-01
2069-12-01
2070-01-01
2070-02-01
2070-03-01
2070-04-01
2070-05-01
2070-06-01
2070-07-01
2070-08-01
2070-09-01
2070-10-01
2070-11-01
2070-12-01
2071-01-01
2071-02-01
2071-03-01
2071-04-01
2071-05-01
2071-06-01
2071-07-01
2071-08-01
2071-09-01
2071-10-01
2071-11-01
2071-12-01
2072-01-01
2072-02-01
2072-03-01
2072-04-01
2072-05-01
2072-06-01
2072-07-01
2072-08-01
2072-09-01
2072-10-01
2072-11-01
2072-12-01
2073-01-01
2073-02-01
2073-03-01
2073-04-01
2073-05-01
2073-06-01
2073-07-01
2073-08-01
2073-09-01
2073-10-01
2073-11-01
2073-12-01
2074-01-01
2074-02-01
2074-03-01
2074-04-01
2074-05-01
2074-06-01
2074-07-01
2074-08-01
2074-09-01
2074-10-01
2074-11-01
2074-12-01
2075-01-01
2075-02-01
2075-03-01
2075-04-01
2075-05-01
2075-06-01
2075-07-01
2075-08-01
2075-09-01
2075-10-01
2075-11-01
2075-12-01
2076-01-01
2076-02-01
2076-03-01
2076-04-01
2076-05-01
2076-06-01
2076-07-01
2076-08-01
2076-09-01
2076-10-01
2076-11-01
2076-12-01
2077-01-01
2077-02-01
2077-03-01
2077-04-01
2077-05-01
2077-06-01
2077-07-01
2077-08-01
2077-09-01
2077-10-01
2077-11-01
2077-12-01
2078-01-01
2078-02-01
2078-03-01
2078-04-01
2078-05-01
2078-06-01
2078-07-01
2078-08-01
2078-09-01
2078-10-01
2078-11-01
2078-12-01
2079-01-01
2079-02-01
2079-03-01
2079-04-01
2079-05-01
2079-06-01
2079-07-01
2079-08-01
2079-09-01
2079-10-01
2079-11-01
2079-12-01
2080-01-01

## XH-01
log_name | start_time | end_time | mission_detail | sub_log | duration | status | location
Construction | 2050-03-15 | 2052-02-06 | Xihe XH-01 Construction | 2050-03-15 First module delivered to LEO via Vulture Shuttle 2052-02-06 Assembly completed in LEO | 693 | archieved | LEO
Fitting | 2052-02-07 | 2052-05-31 |  |  | 114 | archieved | LEO
Trial Run | 2052-06-01 | 2052-11-30 | Trial Run before commissioning | 2052-06-01 Begin Trial Run in Earth Orbit, testing all systems 2052-11-30 Trial Run complete, all systems perform as expected. Including multiple run to GEO and Lunar Orbit before returning to LEO. | 182 | archieved | Earth
Maintenance | 2052-12-01 | 2053-01-05 |  |  | 35 | archieved | Earth
Deep Space Test Mission | 2053-01-12 | 2053-12-18 | Long term uncrewed test | 2053-01-12 Uncrewed mission to Earth-Sun L2 point to test deep space operations 2053-12-18 Back to LEO | 340 | archieved | Earth-Sun L2
Maintenance and upgrades | 2054-01-07 | 2054-06-28 |  |  | 172 | archieved | LEO
Mars Mission Demo Outbound | 2054-07-10 | 2054-08-21 | Earth-Mars transfer, Uses standard trajectory with 102km/s of departure burn |  | 42 | archieved | Sun
Mars Mission Demo at Mars | 2054-08-21 | 2055-01-10 | Uncrewed, Deliver the first Mars-One base construction equipment package to Mars orbit. | 2054-08-21 Mars Orbit Arrival, deploy equipment package to Mars surface via lander 2055-01-10 Mars Departure, return to Earth | 142 | archieved | Mars
Mars Mission Demo Return to Earth | 2055-01-10 | 2055-02-28 | Uses standard trajectory with 97km/s of departure burn | 2055-02-28 Earth Arrival, demo run complete, all systems perform as expected. | 49 | archieved | Sun
Maintenance and upgrade | 2055-03-01 | 2055-05-14 |  |  | 74 | archieved | LEO
Mars One base construction mission 1 outbound | 2055-06-15 | 2055-07-30 | Earth-Mars transfer, Uses standard trajectory with 115km/s of departure burn | 2055-06-15 Picking up crew for Mars One base construction mission 1 2055-06-18 Earth Departure for Mars | 45 | archieved | Sun
Mars One base construction mission 1 at Mars | 2055-07-30 | 2056-02-07 | First Crewed mission to Mars. Construction for Mars One base begin | 2055-07-30 Mars Arrival, begin base construction 2056-02-07 Mars Departure, return to Earth. First to use quick return trajectory. | 192 | archieved | Mars
Mars One base construction mission 1 Return to Earth | 2056-02-07 | 2056-03-18 | Mars-Earth transfer. Uses Fast-travel trajectory with 207km/s of departure burn | 2056-03-18 Earth Arrival, crew return |  | archieved | Sun
Maintenance and upgrades | 2056-03-25 | 2056-06-20 |  |  | 87 | archieved | LEO
Mars One base construction mission 3 | 2056-07-30 | 2056-09-15 | Earth-Mars transfer. Uses standard trajectory with 95km/s of departure burn | 2056-07-30 Picking up crew for Mars One base construction mission 3 2056-08-02 Earth Departure for Mars | 47 | archieved | Sun
Mars One base construction mission 3 | 2056-09-15 | 2057-02-12 | Third Mars One base construction. First crew hand-off on Mars(with Mars One base construction 2). | 2056-09-15 Mars Arrival, continue base construction 2057-02-12 Mars Departure, return to Earth. | 150 | archieved | Mars
Mars One base construction mission 3 | 2057-02-12 | 2057-03-25 | Mars-Earth transfer. Uses standard trajectory with 122km/s of departure burn | 2037-03-25 Earth Arrivasl, crew return | 41 | archieved | Sun
Maintenance | 2057-03-26 | 2057-04-25 |  |  | 30 | archieved | LEO
Mars Expedition 2 Outbound | 2057-05-05 | 2057-06-22 | Earth-Mars transfer using standard trajectory with 110km/s of departure burn | 2027-05-05 Picking up crew for Mars Expedition 2 2027-05-09 Earth Departure for Mars | 48 | archieved | Sun
Mars Expedition 2 at Mars | 2057-06-22 | 2058-04-18 | Second long term Mars Expedition, first mission to Mars One base after the construction is completed. First mission involving space tourism to Mars. | 2057-06-22 Mars Arrival 2057-06-25 Mars EDL and surface operations begin 2058-04-10 Begin Mars Departure preparations 2058-04-18 Mars Departure for Earth | 300 | archieved | Mars
Mars Expedition 2 Return to Earth | 2058-04-18 | 2058-05-20 | Mars-Earth transfer using standard trajectory with 115km/s of departure burn | 2058-04-18 Mars Departure for Earth 2058-05-20 Earth Arrival, crew return | 32 | archieved | Sun
Maintenance | 2058-05-21 | 2058-06-18 |  |  | 28 | archieved | LEO
Europa Expedition 1 Outbound | 2058-07-10 | 2058-09-25 | Earth-Jupiter transfer using standard trajectory with 160km/s of departure burn | 2058-07-10 Picking up crew for Europa Expedition 1 2058-07-12 Earth Departure for Jupiter system 2058-09-25 Europa Arrival | 77 | archieved | Sun
Europa Expedition 1 at Jupiter System | 2058-09-25 | 2059-07-10 | First standard crew expedition to Europa Outpost to begin exploration of Jupiter system Long term surface operation at Europa Outpost, followed by exploration of IO and Ganymede | 2058-09-25 Europa Arrival 2058-09-27 Europa descend, begin surface operation at Europa Outpost 2058-12-15 Europa ascend, begin Jupiter system exploration 2058-12-20 Begin IO exploration 2059-01-20 Return to Europa Outpost 2059-06-20 Begin Europa Outpost departure preparations 2059-06-25 Europa Expedition 1 crew ascend from Europa Outpost 2059-07-05 begin Ganymede exploration 2059-07-10 Departure for Earth, upgrade planned. | 288 | archieved | Europa
Europa Expedition 1 Return to Earth | 2059-07-10 | 2059-11-15 | Uses standard trajectory with 112km/s of departure burn Parked to Star Port | 2059-07-10 Departure for Earth. 2059-11-15 Earth Arrival, Park to Star Port. | 128 | archieved | Sun
Maintenance and upgrade | 2059-11-16 | 2060-02-19 | Greenhouse upgrade to support long term deep space missions |  | 95 | archieved | LEO
Europa Expedition 3 Outbound | 2060-02-20 | 2060-05-22 | Uses standard trajectory with 163km/s of departure burn | 2060-02-20 Picking up Europa Expedition 3 crew, On its way to explore Jupiter systems before sending crew to Europa Outpost | 92 | on-going | Sun

## ST-01
log_name | start_time | end_time | mission_detail | sub_log | duration | status | location
Construction | 2050-09-15 | 2053-02-02 |  |  | 871

## Model
log_name | start_time | end_time | mission_detail | sub_log | duration | status | location